## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Python
INTERN NAME: | Rakshitha Shetty
PROJECT NAME: | Student Data Analysis Using Python
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-12-22

## LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | ENTERPRISE AI-POWERED SDLC ASSISTANT
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2025-12-25 | Voice recognition accuracy dropped to 70% during testing | Voice Input Technology | Yes | Implement noise reduction, improve audio processing | Added audio preprocessing algorithms, fallback text input | Student (Intern) | Solved | User environment testing crucial
2 | 2025-12-28 | Groq API rate limiting caused service interruptions | AI Integration | Yes | Implement caching, multiple providers | Added response caching, error handling, fallback system | Student (Intern) | Solved | API monitoring essential
3 | 2025-12-31 | WebSocket connections failing on slow networks | Real-time Communication | Yes | Connection retry logic, HTTP fallback | Implemented retry mechanism, fallback polling | Student (Intern) | Solved | Network resilience critical
4 | 2026-01-05 | Context management affecting conversation continuity | AI Context Management | Yes | Simplified context storage, history management | Redesigned context storage, improved history tracking | Student (Intern) | Solved | Complex systems need iteration
5 | 2026-01-12 | Browser compatibility issues with Firefox voice input | Cross-browser Support | Yes | Progressive enhancement, clear warnings | Added browser detection, compatibility warnings | Student (Intern) | Solved | Browser limitations must be addressed early