## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | ENTERPRISE AI-POWERED SDLC ASSISTANT
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE
EXPECTED COMPLETION DATE
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop an intelligent, voice-enabled AI assistant that provides real-time guidance throughout the entire Software Development Lifecycle, improving development efficiency by 30% and standardizing best practices across all teams while integrating seamlessly with existing project management tools.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | This project addresses critical gaps in development team productivity by replacing manual knowledge searches with instant AI guidance, reducing decision-making time and ensuring consistent SDLC implementation. The solution provides measurable ROI through improved efficiency, reduced knowledge transfer costs, and enhanced project quality while requiring minimal investment compared to alternative training solutions.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Performance Goal: Achieve 95% voice recognition accuracy with sub-3-second AI response times by January 18, 2026 Time Goal: Complete full development cycle within 4 weeks using 120 hours of development resources Resource Goal: Utilize single developer with AI/ML expertise to create enterprise-ready solution
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Voice-enabled AI assistant with continuous speech recognition Real-time chat interface with WebSocket communication SDLC-focused AI responses with persona detection Integration APIs for Jira, Trello, and Asana Complete technical documentation and deployment package Comprehensive testing suite with 85% code coverage
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Backend API development with FastAPI and WebSocket support Frontend React application with voice input interface AI integration using Groq LLaMA3 with prompt engineering MongoDB database for conversation persistence JWT authentication and security implementation Comprehensive testing and performance optimization
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Mobile application development (iOS/Android) Advanced machine learning model training Multi-language support implementation Enterprise user management system Advanced analytics and reporting dashboard
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Student(intern) with full-stack and AI/ML expertise
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Development environment and tools Cloud hosting and deployment infrastructure AI API services (Groq LLaMA3) Database services (MongoDB Atlas) Testing and monitoring tools
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | NULL
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Development Team Lead responsible for project delivery and technical decisions
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Software engineers, Project managers, IT leadership
END CUSTOMER (Mention the client name.) | Internal development department seeking to improve SDLC implementation and team productivity
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Voice recognition accuracy issues affecting core functionality AI API rate limits causing service degradation Browser compatibility limitations for voice input Real-time communication failures affecting user experience
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Users have modern browsers supporting Web Speech API Stable internet connection for real-time processing Users will grant microphone access permissions Groq API will remain available and stable
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Browser compatibility for voice input Dependency on external AI service APIs Limited development timeline and resources Single developer resource constraint
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date: 12-21-2025 Requirement gathering marked as complete after submission of SRS document and stakeholder questionnaire responses.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date: 12-27-2025 Planning phase considered complete after submission of Work Breakdown Structure (WBS), Project Schedule and RAID logs.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 01-03-2026 Design stage considered complete after submission of Design Specifications and system architecture documentation.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 01-10-2026 Development stage considered complete after submission of working backend API, frontend interface, and AI integration.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date: 01-16-2026 Testing stage considered complete after submission of Test Reports showing 85% code coverage and performance metrics.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date: 01-17-2026 Deployment stage considered complete after submitting production configuration and successful system deployment.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date: 01-18-2026 Project closure considered complete after handover of lessons learnt log, project report and installation guide.