## guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Raks
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
PROJECT PLAN
PROJECT DOMAIN | Prompt Engg.
PROJECT MANAGER | Harshada Topale
PROJECT START DATE | 2025-12-21
PROJECT END DATE | 2026-01-17
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments
1 | [Week title Eg: Pre IP]
1.1 |  | Data Preparation | Data Understanding | Dataset Review | Dataset Received | Rakshitha | 2023-07-31 | 2023-08-05
1.1.1 |  | [Activity 1.1] | [Task 1.1.1]
1.1.2 |  | [Activity 1.1] | [Task 1.1.2]
1.1.3 |  | [Activity 1.1] | [Task 1.1.3]
1.1.4 |  | [Activity 1.1] | [Task 1.1.4]
1.2 |  | [Activity 1.2]
1.2.1 |  | [Activity 1.2] | [Task 1.2.1]
1.2.1.1 |  | [Activity 1.2] |  | [Sub Task 1.2.1.1] | [Eg: 2.5,2.1.1.5]
1.2.3 |  | [Activity 1.2] | [Task 1.2.3]
2 | [Week title Eg: Pre IP]
2.1
1 | Week 1 | Project Initiation | Internship Onboarding | Orientation and guidelines | None | Self | 2025-12-21 | 2025-12-21 | 2025-12-21 | 4 | Completed | 1 | Internship started
1.1 | Week 1 | Backend Development | API Setup | FastAPI installation & configuration | API Setup | Self | 2025-12-22 | 2025-12-22 | 2025-12-22 | 4 | Completed | 1 | Basic API structure ready
1.2 | Week 1 | Backend Development | API Setup | Route definitions & middleware | API Setup | Self | 2025-12-23 | 2025-12-23 | 2025-12-23 | 4 | Completed | 1 | API endpoints defined
1.3 | Week 1 | Backend Development | Database Integration | MongoDB connection setup | Database | Self | 2025-12-24 | 2025-12-24 | 2025-12-24 | 4 | Completed | 1 | Database connected
1.4 | Week 1 | Backend Development | Database Integration | Model definitions & schemas | Database | Self | 2025-12-25 | 2025-12-25 | 2025-12-25 | 4 | Completed | 1 | Models created
1.5 | Week 1 | Backend Development | Authentication | JWT token system setup | JWT Setup | Self | 2025-12-26 | 2025-12-26 | 2025-12-26 | 4 | Completed | 1 | Auth system ready
1.6 | Week 1 | Backend Development | Authentication | User registration & login | JWT Setup | Self | 2025-12-27 | 2025-12-27 | 2025-12-27 | 4 | Completed | 1 | User auth working
2 | Week 2
2.1 | Week 2 | Frontend Development | HTML Setup | Project initialization & routing | Backend API | Self | 2025-12-29 | 2025-12-29 | 2025-12-29 | 4 | Completed | 1 | HTML structure ready
2.2 | Week 2 | Frontend Development | HTML Setup | Component structure & state management | Html Setup | Self | 2025-12-30 | 2025-12-30 | 2025-12-30 | 4 | Completed | 1 | Components organized
2.3 | Week 2 | Frontend Development | UI Components | Chat interface design | Html Setup | Self | 2025-12-31 | 2025-12-31 | 2025-12-31 | 4 | Completed | 1 | Chat UI ready
2.4 | Week 2 | Frontend Development | UI Components | Voice input button & feedback | Chat UI | Self | 2026-01-01 | 2026-01-01 | 2026-01-01 | 4 | Completed | 1 | Voice button functional
2.5 | Week 2 | AI integration | LLM Setup | Groq API integration | UI Components | Self | 2026-01-02 | 2026-01-02 | 2026-01-02 | 4 | Completed | 1 | AI responses working
2.6 | Week 2 | AI integration | LLM Setup | Prompt engineering & testing | LLM Setup | Self | 2026-01-03 | 2026-01-03 | 2026-01-03 | 5 | Completed | 1 | Professional responses
3 | Week 3
3.1 | Week 3 | Voice Input | Speech Recognition | Web Speech API implementation | UI Components | Self | 2026-01-05 | 2026-01-05 | 2026-01-05 | 4 | Completed | 1 | Voice input functional
3.2 | Week 3 | Voice Input | Speech Recognition | Audio processing & error handling | Speech Recognition | Self | 2026-01-06 | 2026-01-06 | 2026-01-06 | 4 | Completed | 1 | Audio processing ready
3.3 | Week 3 | Voice Input | Continuous Listening | 15s timeout implementation | Speech Recognition | Self | 2026-01-07 | 2026-01-07 | 2026-01-07 | 4 | Completed | 1 | Timeout feature ready
3.4 | Week 3 | Voice Input | Continuous Listening | Text accumulation across pauses | Timeout | Self | 2026-01-08 | 2026-01-08 | 2026-01-08 | 4 | Completed | 1 | Text accumulation working
3.5 | Week 3 | AI Enhancement | Prompt Engineering | SDLC-specific prompts design | LLM Setup | Self | 2026-01-09 | 2026-01-09 | 2026-01-09 | 4 | Completed | 1 | SDLC prompts ready
3.6 | Week 3 | AI Enhancement | Prompt Engineering | Persona detection & context | Prompts | Self | 2026-01-10 | 2026-01-10 | 2026-01-10 | 5 | Completed | 1 | Context-aware responses
4 | Week 4
4.1 | Week 4 | WebSocket Integration | Real-time Chat | WebSocket server setup | Voice Input | Self | 2026-01-12 | 2026-01-12 | 2026-01-12 | 4 | Completed | 1 | WebSocket server ready
4.2 | Week 4 | WebSocket Integration | Real-time Chat | Client-side WebSocket integration | WebSocket Server | Self | 2026-01-13 | 2026-01-13 | 2026-01-13 | 4 | Completed | 1 | Real-time messaging
4.3 | Week 4 | Testing | Unit Testing | Backend API testing | WebSocket | Self | 2026-01-14 | 2026-01-14 | 2026-01-14 | 4 | Completed | 1 | API tests passing
4.4 | Week 4 | Testing | Unit Testing | Frontend component testing | Backend Tests | Self | 2026-01-15 | 2026-01-15 | 2026-01-15 | 5 | Completed | 1 | Component tests ready
4.5 | Week 4 | Testing | Integration Testing | End-to-end voice-to-AI testing | Unit Tests | Self | 2026-01-16 | 2026-01-16 | 2026-01-16 | 4 | Completed | 1 | Full pipeline tested
4.6 | Week 4 | Testing | Integration Testing | Performance & load testing | Integration Tests | Self | 2026-01-17 | 2026-01-17 | 2026-01-17 | 5 | Completed | 1 | Performance optimized
Sr No,Week/Phase,Activities,Task,Sub Task,Dependencies,Assigned To,Start Date,End Date,Actual End Date,Hours Required,Status,Progress,Comments
1,Week 1 - Data Preparation,Data Understanding,Dataset Review,,Dataset Received,Student,22-Dec-23,24-Dec-23,24-Dec-23,10,Completed,100%,Initial dataset understanding
1.1,Week 1 - Data Preparation,Data Understanding,Import Dataset,Excel to Python,Python Setup,Student,22-Dec-23,22-Dec-23,22-Dec-23,2,Completed,100%,Dataset loaded successfully
1.2,Week 1 - Data Preparation,Data Understanding,Check Shape & Info,,Dataset Import,Student,23-Dec-23,23-Dec-23,23-Dec-23,2,Completed,100%,Rows and columns verified
1.3,Week 1 - Data Preparation,Data Understanding,Column Identification,,Data Loaded,Student,23-Dec-23,23-Dec-23,23-Dec-23,2,Completed,100%,Columns analyzed
1.4,Week 1 - Data Preparation,Data Understanding,Remove Duplicates,Email ID Check,Data Inspection,Student,24-Dec-23,24-Dec-23,24-Dec-23,2,Completed,100%,Duplicate records removed
2,Week 2 - Data Cleaning,Data Cleaning,Handle Missing Values,,Clean Dataset,Student,25-Dec-23,28-Dec-23,28-Dec-23,14,Completed,100%,Data cleaning completed
2.1,Week 2 - Data Cleaning,Data Cleaning,Numeric Null Handling,Median Imputation,Clean Dataset,Student,25-Dec-23,26-Dec-23,26-Dec-23,4,Completed,100%,Numeric values cleaned
2.2,Week 2 - Data Cleaning,Data Cleaning,Categorical Null Handling,Fill Unknown,Clean Dataset,Student,27-Dec-23,27-Dec-23,27-Dec-23,4,Completed,100%,Categorical values cleaned
2.3,Week 2 - Data Cleaning,Data Transformation,Family Income Mapping,Convert to Numeric,Income Ranges,Student,28-Dec-23,28-Dec-23,28-Dec-23,6,Completed,100%,Income standardized
3,Week 3 - Exploratory Data Analysis,EDA,Descriptive Analysis,,Clean Data,Student,29-Dec-23,03-Jan-24,03-Jan-24,20,Completed,100%,EDA completed
3.1,Week 3 - EDA,EDA,Unique Student Count,Email ID Analysis,Clean Data,Student,29-Dec-23,29-Dec-23,29-Dec-23,2,Completed,100%,2157 unique students
3.2,Week 3 - EDA,EDA,Average CGPA Calculation,,CGPA Column,Student,30-Dec-23,30-Dec-23,30-Dec-23,2,Completed,100%,Average CGPA 8.03
3.3,Week 3 - EDA,EDA,Graduation Year Analysis,,Year Column,Student,31-Dec-23,01-Jan-24,01-Jan-24,4,Completed,100%,Year-wise analysis
3.4,Week 3 - EDA,Visualization,Charts & Graphs,Bar Box Scatter,Matplotlib Seaborn,Student,02-Jan-24,03-Jan-24,03-Jan-24,6,Completed,100%,Visualizations created
4,Week 4 - Insights & Documentation,Analysis,Correlation Analysis,Heatmap,Numeric Data,Student,04-Jan-24,05-Jan-24,05-Jan-24,6,Completed,100%,Correlation identified
4.1,Week 4 - Insights,Analysis,Salary vs Skills,CGPA & Python Exp,EDA Results,Student,06-Jan-24,06-Jan-24,06-Jan-24,3,Completed,100%,Trends observed
4.2,Week 4 - Documentation,Documentation,Final Report,Conclusion & Insights,Analysis Complete,Student,07-Jan-24,07-Jan-24,07-Jan-24,4,Completed,100%,Final report submitted
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you